## Sprint-1.0 Retrospection
Project Name: Tesla sapHybris
Sprint - 1.0 |  | Date: 30-mar-2023
# | +ve | r | Action Item | Target Date | Responsible
1 | 70% of the planned tasks are completed in Sprint - 1.0 | Taking lot of time to complete a single task | Team Members should divide the task with proper planning | 30-Mar-2023 (Sprint - 1.0) | Team
2 | Team co-ordination is excellent | No delta as of now | Tasks are understood by each team member | 30-Mar-2023 (Sprint - 1.0) | Team
3 | Received help from seniors | Not able to do some tasks | Team Members should get guidance from collegaues and seniors | 30-Mar-2023 (Sprint - 1.0) | Team
4 | Extending work hours for the project | Need some time for R&D | Tasks can be completed on time | 30-Mar-2023 (Sprint - 1.0) | Team
5 | Proper database connection | Sometimes data fetching is failed due to network connection | Dealer data is displayed to the user | 30-Mar-2023 (Sprint - 1.0) | Team
6 | Running impex and executing | No delta as of now | Queries can be handled easily | 30-Mar-2023 (Sprint - 1.0) | Team
7 | Frontent deployment done in Azure app service | Limited Azure Subscription | Can be used in production | 30-Mar-2023 (Sprint - 1.0) | Team