## Product Backlog
Final PoC Project | [6 empty] | Story point estimation
# | REQ ID | Features / Requirements - Level 1 | Features / Requirements - Level 2 | Release Phase/Milestone | Priority | Status | Initial Estimation | Sprint |  | Remarks
[7 empty] | 0 | 1 | 2
[7 empty] | 768 | 23 | 14
Home Page
1 | REQ1 | Dashboard
|  |  | Header | Release-1 | P1 | In-Progress | 20 | 1
|  |  | Banner | Release-1 | P1 | In-Progress | 10 | 1
|  |  | Services we provide | Release-1 | P1 | In-Progress | 10 | 1
|  |  | Contact Us | Release-1 | P1 | In-Progress | 20 | 1
|  |  | Footer | Release-1 | P1 | In-Progress | 22 | 1
Application Management for dealer
2 | REQ2 | Signup and signin
|  |  | request made by the new dealer | Release-1 | P1 | In-Progress | 20 | 1
|  |  | login | Release-1 | P1 | In-Progress | 23 | 1
3 | REQ3 | Display product
|  |  | display produts available in each city | Release-1 | P2 | In-Progress | 25 | 1
|  |  | Filter products | Release-1 | P2 | In-Progress | 30 | 1
4 | REQ4 | Product description page
|  |  | view the selected product | Release-1 | P2 | In-Progress | 20 | 1
|  |  | add to cart | Release-1 | P2 | In-Progress | 32 | 1
|  |  | checkout or continue shopping | Release-1 | P2 | In-Progress | 20 | 1
5 | REQ5 | Payment
|  |  | price calculation | Release-1 | P3 | In-Progress | 35 | 1
|  |  | Mode of payment | Release-1 | P2 | In-Progress | 45 | 1
|  |  | order summary | Release-1 | P3 | In-Progress | 25 | 1
Application Management for dealer admin
6 | REQ6 | Dealer admin login
|  |  | verify whether the dealer exists | Release-1 | P1 | In-Progress | 15 | 1
7 | REQ7 | Dealer admin dashboard
|  |  | Accept or reject newly registered dealers | Release-1 | P2 | In-Progress | 24 | 1
|  |  | track activities of dealers | Release-1 | P3 | In-Progress | 25 | 1
8 | REQ8 | Book a test drive (done by frontend)
|  |  | Design to select car model | Release-1 | P1 | Completed | 5 | 1
|  |  | Add basic details | Release-1 | P1 | Completed | 5 | 1
|  |  | Footer | Release-1 | P3 | Completed | 2 | 1
|  |  | Fetching dealers details from DB | Release-1 | P2 | In-Progress | 10 | 1
|  |  | Displaying Available dealers | Release-1 | P2 | In-Progress | 12 | 1
9 | REQ9 | Continous Integration (done by DevOps)
|  |  | Creation of boards in azure devops | Release-1 | P3 | Completed | 3 | 1
|  |  | CI Pipeline for Frontend | Release-1 | P1 | Completed | 5 | 1
|  |  | Deployment in app service | Release-1 | P2 | In-Progress | 5 | 1
Application management for customer
10 | REQ10 | Book a test drive
|  |  | Enter required information | Release-2 | P1 | Not Started | 23 |  | 2
|  |  | Select available dealers | Release-2 | P1 | Not Started | 45 |  | 2
|  |  | Request for test drive | Release-2 | P1 | Not Started | 36 |  | 2
Application management for Tesla Admin
11 | REQ11 | Tesla admin login
|  |  | verify whether the tesla admin exists | Release-2 | P2 | Not Started | 24 |  | 2
12 | REQ12 | Tesla admin dashboard
|  |  | accept or reject request for test drive | Release-2 | P1 | Not Started | 66 |  | 2
|  |  | add, update and remove accessories | Release-2 | P1 | Not Started | 62 |  | 2
|  |  | view all the request made by customers | Release-2 | P3 | Not Started | 44 |  | 2
13 | REQ13 | Dealer Admin (done by frontend)
|  |  | Login of individual dealer admin | Release-2 | P1 | Not Started | 10 |  | 2
|  |  | accept or reject request for test drive | Release-2 | P1 | Not Started | 12 |  | 2
|  |  | view all the request made by customers | Release-2 | P3 | Not Started | 20 |  | 2

## Burndown
Iteration | 0 | 2
Remaining | 768 | 0

## Release Phase
# | Release Phase/Milestone | Description
1 | Release-1 | Sprint-1 Release
2 | Release-2 | Sprint-2 Release