## Sprint-2.0 Retrospection
Project Name: Tesla sapHybris
Sprint - 2.0 |  | Date: 07-Apr-2023
# | +ve | r | Action Item | Target Date | Responsible
1 | 95% of the planned tasks are completed in Sprint - 1.0 | Custom extensions not working | Team Members should divide the task with proper planning | 7-Apr-2023 (Sprint - 2.0) | Team
2 | Page layout | Customization does not work | Adjusted using the layout | 7-Apr-2023 (Sprint - 2.0) | Team
3 | Received help from seniors | Not able to do some tasks | Team Members should get guidance from collegaues and seniors | 7-Apr-2023 (Sprint - 2.0) | Team
4 | Extending work hours for the project | Need some time for R&D | Tasks can be completed on time | 7-Apr-2023 (Sprint - 2.0) | Team
5 | Tesla admin and super admin done | Not able to distinguish between them | Both dealer's dashboard is displaying separately | 7-Apr-2023 (Sprint - 2.0) | Team
6 | Running impex and executing | No delta as of now | Queries can be handled easily | 7-Apr-2023 (Sprint - 2.0) | Team
7 | CI using Jenkins | Limited Azure Subscription | Can be used in production | 7-Apr-2023 (Sprint - 2.0) | Team